## Slide 1: Weekly Report – 2026 WK28
HungFu Lin
AMMS/MWC/TD&SW

## Slide 2: Status report
ID # | Status | Event Description | Plan |  | Actual | To-do & Status update
 |  |  | Start | End | Finish | 
1 | Done | [WM2308-EXT1] – RFDate Test Log Converter | 6/1 | 6/2 | 6/2 | 1. Modify RX-Blocking translation rule. (Done)
2 | Ongoing | [WM2308/WM2305] – TD support –Octavia tool | 7/6 | 7/10 | 7/10 | Release Octavia tool v3.4.0 and v3.4.1 (Done) 1. NR1 一律追加 [VR] 欄位；值依 MpFuse／SafeFuse 分別控制 2. NR1 CHKROUT 前置：向 SFIS 反查 BDID／FUSELVL 並比對（step6） 3. mfg_info.ini 自動掃描組數（不再依賴Work_Order_Pairs） 4. GUI新增SFIS回應非OK#/FAIL#的待確認資料（保留補送 / 作廢封存） 5. 修正 step6 反查 Chkrout_Query_Interval=1 失效 6. step6 反查查詢字串由「三筆」改為「兩筆（PN 版／MO 版）」 7. 修正GUI主畫面被截字 Develop Octavia tool v3.5.0 – for PRQ case.
3 | Ongoing | [Miscellaneous] – New transmission platform between ATE&SFIS | 6/29 | 7/10 |  | Add project module and config.(Ongoing) Trail run all projects.(2035NR…2308T1_OQC) - ATE to Mars, Mars to SFIS, SFIS to Mars.

## Slide 3: Status report
ID # | Status | Event Description | Plan |  | Actual | To-do & Status update
 |  |  | Start | End | Finish | 
4 | Done | [Miscellaneous] – AI coding agent project | 6/29 | 7/3 | 7/3 | SmartQC: AI-Powered Visual Inspection for Unmanned Manufacturing (Done)
5 | Pending | [Miscellaneous] – Adaptive and Modular Test System | 6/15 | 6/25 |  | Architecture Design — Defined a modular 4-layer architecture Manager Responsibility Specification DUT Connection Topology Unified Internal Message Format Add DUT plug in layer. Study the code flow.